## Slide 1: PCE and Strategic planning
The IPPC Secretariat
With the financial support of the STDF project 401
Phytosanitary Capacity Evaluation (PCE) facilitators training

## Slide 2: The project cycle
Identification
Planning
Implementation
Monitoring & Evaluation

## Slide 3: STRATEGIC PLANNING PROCESS
Needs assessment
Stakeholder analysis
Problem Identification
Strategic Planning
Problem analysis (Cause and Effect)
SWOT analysis
Logical Framework
Action Planning
Prioritisation of actions
Work plan development
Resource mobilisation

## Slide 4: Stakeholder analysis
Type of participation Stage in cycle | Inform | Consult | Partnership | Control
Identification |  |  | Donor, Technical Units | 
Planning | External Stakeholders | Secondary stakeholders |  | 
Implementation | Donors | External Stakeholders | Donors, Secondary stakeholders, Primary stakeholders | Project leaders
Monitoring & Evaluation | Donors | Secondary stakeholders | Project leaders, Secondary stakeholders, Primary stakeholders | External consultants

## Slide 5: Needs assessment/Situation or GAP analysis
Questionnaires
Surveys
Focus groups
Formal Consultations
External consultants assessments
Evaluation tools/methods
Integrated methods
…

## Slide 6: Problem analysis (Cause and Effect)
Secondary Cause | Primary Cause | Weakness | Primary Consequence | Secondary Consequence
 |  | There is a human resource problem for export certification in XYZ | Delay in the issuance of phytosanitary certificates | Increased exporters complains

## Slide 7: SWOTs
Strengths | Weakness | Opportunities | Threats | Actions
Export development strategy is in place | There is a human resource problem for export certification in XYZ | Money from private sector investment available | Private sector support lack luster because they are not confident in the services provided by the NPPO | 

## Slide 8: Logical Framework
Result chain |  | Indicators | Means of verification | Assumptions and/or risks
Goal | National plant resources protected |  |  | 
Purpose or objective | An improved integrated phytosanitary system |  |  | 
Outputs or results expected | 1. 2. 3. 4. |  |  | 
Activities | 1.1 2.1 3.1 4.1 |  |  | 

## Slide 9: WORKPLAN
Outputs | Activity (s) | Sub-Activity (s) | costs | Responsible entity | deadline
Output 1 | 1.1 | 1.1.1 |  |  | 
 | 1.2 … | 1.2.1 … |  |  | 
Output 2 | 2.1 | 2.1 |  |  | 
Output 3 | 3.1 | 3.1 |  |  | 
Output 4 | 4.1 | 4.1 |  |  |