Written updates form the members on Sea Containers Task Force 2021 Work Plan

## (Last updated 2021-04-27)

| Output/Work Area I - NPPO Surveys |  |  |  |
| --- | --- | --- | --- |
| Expected outcome: Data on the degree of interior and exterior contamination of a subset of empty and packed (with cargo) sea containers, as well as their cargoes, utilizing a uniform approach. |  |  |  |
| Action Item | Action Party | 2021 | Updates |
| - NPPOs provide survey results and analysis of their national surveys to the SCTF | Wendy, Wendy, Sina, Gu, Rama, Frederick | September-October 2021 | China has indicated that due to security reasons they might not be in a position to submit data. Frederick: Summary (annexed to this paper) from a preliminary report survey for sea containers in Kenya which was conducted between July 2021 and February 2021. The survey is ongoing as part of our unscheduled border inspections and surveillance. The final report will be availed once completed. Wendy Beltz: The U.S. and Canada have been unable to conduct proper surveys. We’re still working with our border services agencies and hope to conduct surveys in the future Guanghao Gu (Grace): The surveys has not been carried out in China |
| - Consider deletion of some fields from the inspection template of the Guidelines on Sea Container Surveys for NPPOs to assist in better reporting | Rama/All | February 2021 | This might facilitate improved reporting by some countries Contact China on what exactly to delete, otherwise delete 1.2 Rama: subject to any feedback from members on sensitive fields to be deleted for better reporting, I am happy to make the necessary adjustments to the field record of the Survey Guideline Guanghao Gu (Grace): What I mentioned in October 2020 is not mean some fields can not be shared. In fact, GACC pays great attention to data security especially at that time. So the submission of new data may become very difficult, but we will try our best to apply for it . I have no proposals on changing the database. So this can be deleted |
| - Develop a paper summarizing the pest risks resulting from NPPO surveys | Wendy, Wendy, Sina, Gu, Rama, Frederick | November 2021 | Can be communication tool Rama: subject to receiving survey results from NPPOs Wendy Beltz: The U.S. and Canada have been unable to conduct surveys so we’re not able to publish a paper at this time. Guanghao Gu (Grace): China has been unable to conduct proper surveys so we’re not able to publish a paper at this time. We have a paper summarizing the pest risk resulting from Statistics and analysis of historic interception data from 2003-2017 |
| - Collect information on techniques used by NPPOs, port authorities/other stakeholders to survey and monitor cleanliness, safety and movement of CTUs | All | Over the course of 2021 | Australia has initiated a project on development of technologies. Rama might be in a position to lead this. Information could assist in finding ways to reduce the cost of surveys. |
| - The World Bank to update the SCTF on the pilot to support selected CPs /NPPOs with national surveys | Shane | September- October 2021 | Update will be delivered at December 2021 meeting Shane: The World Bank is continuing to engage with countries in the Pacific to discuss ways to implement the survey. Fiji has indicated that it very supportive of undertaking the surveys and is looking for technical assistance. We plan to engage with them in the coming weeks. |
| - Consider assistance to IMO member countries on sea container cleanliness in the IMO technical development programmes | IMO/IPPC Secretariats | November 2021 | Depends on the outcomes of the work from the Correspondence Group on the inspection programme Bingbing: no further updates on this matter |
| Output/Work Area II - Coordination with CPs, RPPOs, industry and other organizations |  |  |  |
| Expected outcome: Enhanced collaboration on identification of pest risks and on possible international actions as well as consistency of relevant regulations with the CPM Recommendation related to sea containers. |  |  |  |
| Action Item | Action Party | 2021 | Comments |
| - Establish collaboration with the International Association of Ports and Harbours (IAPH) |  | Over the course of 2021 | Secretariat will provide update at March 2021 meeting |
| - Work within the CCC CG on refinement of proposals for inclusion of cleanliness and pest management issues into the IMO inspection programme | Secretariat/ All | February 2021 | The proposal for the 4th round of consultation has been submitted in January 2021.The 4th Round has just opened with a submission deadline of March 2, 2021. Wendy Beltz: The U.S. and Canada have been participating with the correspondence groups in our respective countries. Artur: The proposal for the 5th round of consultation has been submitted in March 2021. The report of the CCC 7 proposes several options for revision and most of the members are supporting option A, which has proposals for inclusion of contamination and relevant amendments. Intensive discussion was around making references to ‘pest’ ‘visible’ ‘recontamination’ and ‘appropriate national’. One key issue which arose during the development of the draft option A text was the use of, and definition of, the term ‘pest’. During the discussions of the group the following views where expressed: - A separate definition of pest makes it seem that pests are different from a contaminant, when pests are contaminants of major concern to plant health. - Support removal of the word “pest” prefer simply saying contamination; as it is well defined. Pests are part of the contamination definition although not specifically identified. Focusing on “pest contamination” could inadvertently result in soil and plant debris being overlooked in inspection and reporting. - Retention of “pest” before “contamination” to ensure that the inspection team understands that what is to be inspected for is visible pest contamination, not contamination by e.g. oil, paint etc. and - The current draft definition of ‘contamination’ to be utilised to define the term ‘pest contamination’ and the term ‘pest contamination’ to be used through the draft document replacing the word ‘contamination’ New Zealand proposing a commenting paper which proposes new text to deal with the issue of ‘pest contamination’ and key proposal is to use the term ‘pest contamination’ in place of ‘contamination’ and the insertion of two ways to deal with ‘visible’, a definition of visible or a footnote explaining visible. New Zealand is also looking for co-sponsor the paper as well as collecting views on the options for visible before 21 May. For example, one of the highlights in the proposed option A is: Insert "Pest Contamination" at the end of the list of items to check during the inspection Reporting form 7 Insert new row at appropriate position. - Pest Contamination (number of CTUs found with pest contamination) |
| - Develop a proposal to include additional data fields to the WCO data model | Rama and Sina | 2021 | Consultation with industry to seek input on this has been delayed due to COVID restrictions. Further update will be at March 2021 meeting Rama: Upon further internal discussions, it has been identified that the scope of the additional data fields needs to be determined by the SCTF group – whether the scope is limited to purely capturing information on container cleanliness (for example, is the internal surface of the container free from biosecurity risk material at the time of packing?) or is it also to obtain additional detail to support compliance based frameworks such as the AEO framework? It would be useful to discuss and agree on the scope at the next SCTF meeting. |
| - Industry representatives identify challenges and ways to provide information to be reflected in a WCO data model so that NPPOs can consider this when/if a potential new data element is added in the WCO Data Model | Lars, Uffe, Jiang | 2021 | From Lars: Industry representatives can only meaningfully provide comments if/when a potential data element has been identified. Lars: The position remains the same, i.e. industry can only meaningfully comment if/when a potential data element(-s) has been identified. The SCTF had an extensive discussion of provision of information, and who in the international supply chain would be in the best position to do so, at its September 2019 meeting in Baltimore. The conclusions from that discussion remain valid. |
| - IPPC Sect. discusses with WCO Sect. the inclusion of phytosanitary aspects/criteria into the global AEO framework | Secretariat/WCO Secretariat | 2021 | Ongoing. Ozlem: At the SAFE Review Meeting and SAFE Working Group meeting, the WCO Members and observers discussed all proposals received for SAFE Review Cycle 2021. There were three proposals relevant to the work of the SCTF. - Proposal 1.4 by IPPC-WCO Action Plan: Explore the feasibility of enhancing the AEO programme by adding/including requirements that other border agencies may enforce. Explore the feasibility of enhancing the AEO programme by adding/including requirements that other border agencies may enforce. - Proposal 1.5 by TURKEY: Cooperation with Other Government Agencies Adding the following point in Page 32, under the heading; “2.1.7. Cooperation between Customs and agriculture-food agencies” - Joint Proposal 4.1 by the United States / Guatemala / World BASC In Annex IV, Section G (Cargo Security), add an additional requirement (n) for AEOs, stating that, the AEO shall: n. Implement appropriate measures in accordance with the AEO’s business model, designed to prevent visible pest contamination to include compliance with Wood Packaging Materials (WPM) regulations. Visible pest prevention measures must be adhered to throughout the supply chain. Measures regarding WPM must meet the International Plant Protection Convention’s (IPPC) International Standards for Phytosanitary Measures No. 15 (ISPM 15). The outcomes of the discussions for these three proposals are briefly outlined below; Proposal 1.4 and Proposal 1.5 These two proposals have been discussed together. The SAFE Working Group has been invited to continue to work with Turkey to further develop the guidelines that might include the following (this task will go beyond 2021): - Facilitation measures that can be provided by OGAs (such as Product Safety, Agriculture, Health…authorities) to AEO Programmes. - Effective ways of harmonizing border controls between customs and OGAs. - Member experiences regarding such initiatives. - Possible capacity-building efforts for Member Administrations (within the jurisdiction of Capacity Building Committee). Proposal 4.1 There were a number of Members who expressed their concern regarding the appropriateness of this proposals and its relevance to the SAFE Framework of Standards. It was agreed that the proposal require more discussion to develop a position of consensus and that the proposal will therefore be deferred from this review cycle to the next review cycle. |
| - Participate in the 5th WCO Global AEO conference “AEO 2.0: Advancing towards new horizons for sustainable and secure trade” planned for April 2021 | Secretariat | April 2021 |  |
| - Participate in development of UNECE CTU Code App | Secretariat/Lars All | 2021 | Subject - Establishment of a UNECE expert group. app could provide guidance to CTU packers, could include guidance on prevention of contamination by pests. Lars: There is no progress to report regarding the development of an UNECE CTU Code app. I understand that the ILO’s Sectoral Advisory Bodies (SABs) did not support the establishment of the Group of Experts on the CTU Code at the meeting which took place on 13-15 January 2021. This means that the ILO-IMO-UNECE Group of Experts on CTU Code cannot be established before the next meeting and a supportive decision of the ILO SABs in 2023. This further means, as per WP.24 decision at the 63rd session (ECE/TRANS/WP.24/147, para 80), that the UNECE Secretariat would proceed with arrangements for informal pre-work and organise informal gatherings on the tasks agreed for the pre-work. However, I am not aware that such arrangements for informal pre—work have been communicated to the various stakeholders. |
| - Development of an SCTF proposal for the revision of the CTU Code with respect to pest risks | All/Secretariat | Over the course of 2021 | Artur: UNECE secretariat arranged for a hybrid (in-person and through webex) informal meeting on the CTU Code in English only to take place on 27 and 28 May 2021 with a schedule on both days between 11:00 and 15:00 CET. The provisional agenda for this informal meeting annexed to this paper. As per WP.24 decision at its 62nd session, the agenda covers items agreed for the informal pre-work. The documents referred in the agenda can be consulted at https://unece.org/transport/events/wp24-working-party-intermodal-transport-and-logistics-63rd-session To register to this first informal meeting on the CTU Code and also invite to forward this message to experts who may be interested in joining the first informal meeting and the pre-work. To register, please go to https://uncdb.unece.org/app/ext/meeting-registration?id=wjN8n6 Please note that only registered experts will receive the webex link to the meeting. |
| - Additional contributions to UNECE handbook on national master plans for freight transport and logistics | All | 2021 | As needed |
| - Utilize information from RPPOs with regards to Containers contamination | RPPO/Secretariat | September 2021 | NAPPO has a good example Nico: No information on container contamination and cleanliness is available in the Europe region |
| Output/Work Area III - Communication and awareness raising |  |  |  |
| Expected outcome: Increased awareness of different stakeholders on sea container pest risks through provision of information and possible risk management |  |  |  |
| Action Item | Action Party | 2021 | Comments |
| - Develop regional communication strategy on the need for NPPO surveys and share with the RPPOs to be used for informing CPs in their regions | Sina, Stephanie, Nico RPPOs | January 2021 | The RPPOs should be informed on the availability of the draft communication strategy by the RPPO representative to the SCTF (Sina) Nico: The CPs in the Europe region were informed several times on the need for surveys of container contamination and cleanliness, both by email and orally during meetings. |
| - Publish Information on emerging pest risks in the sea container pathway on the IPP | NPPOs to provide information Secretariat to publish | Over the course of 2021 | Monthly publications would be preferred News Item from Australia was about Khapra beetle posted on IPP on 1st January 2021. Case to be submitted by Mexico (data on Khapra beetle). Calendar for posting could be created, starting from SCTF members submitting one article per month Wendy Beltz: Anecdotal information NASCI has heard during industry webinars Frederick: KEPHIS is also planning for an awareness meeting for stakeholder in the shipping industry in Kenya to sensitize them on the biosecurity risk posed by sea containers |
| - Collaborate with maritime journals to publish cleanliness and emerging pest related articles | All/Secretariat | Over the course of 2021 | Relevant journals could be identified with the assistance of journalists known to be working on these issues Develop an article and assign to SCTF |
| - IPP News item on materials available including industry Quick Guide to the CTU Code and Container Packing Checklist | Secretariat | February 2021 | Lars: An IPP news item on the industry developed CTU Code Quick Guide has been posted on the IPP landing page so these work items can be considered completed. I should add that with the great help and assistance of the NAPPO Secretariat, a Spanish language version was published shortly and noted on the IPP landing page |
| - IPP News item on the progress of the World Bank pilot | Shane | Over the course of 2021 | Depends on the progress of the pilot Shane: Once there is some concrete progress relative to 1.5 raising a news item would follow |
| - IPP News item on the outcomes of the CG work and CCC -7 meeting | Bingbing/Secretariat | September 2021 | Bingbing: happy to contribute on this one and for timing box, it should be “September 2021 |
| - IPP News item on pest risk developed by Industry representatives and published | Lars, Uffe, Jiang | March | From Lars: Industry representatives could develop a news item on the Quick Guide and the Checklist if that would be of interest. Lars: An IPP news item on the industry developed CTU Code Quick Guide has been posted on the IPP landing page so these work items can be considered completed. I should add that with the great help and assistance of the NAPPO Secretariat, a Spanish language version was published shortly and noted on the IPP landing page |
| - IPP News item on survey results developed by countries that conducted surveys | Wendy, Wendy, Sina, Gu, Rama, Frederick | December 2021 | Depends on data availability. Wendy Beltz: Unable to conduct surveys Guanghao Gu (Grace): China has not conducted proper surveys |
| - IPP News Item from NPPOs conducting surveys providing the data on interceptions, information on emerging pests and systems to mitigate pest risks associated with sea containers and their cargos | Wendy, Wendy, Sina, Gu, Rama, Frederick Secretariat to support | One news item per month beginning January 2021 | Wendy Beltz: Unable to conduct surveys Guanghao Gu (Grace): China has not conducted proper surveys |
| - IPP phytosanitary systems page on sea containers develop and published | Secretariat/IC Lead | April-May in 2021 | Artur: The pages contents is developed and reviewed by the IC lead and will be transferred to IT staff in the Secretariat to build the page. |
| - IPP News item on availability of the SCTF landing page | Secretariat | April-May in 2021 | Depends on when SCTF landing page is developed |
| - NPPOs to provide relevant materials to be published on the Sea containers IPP page inter alia case studies | All | Over the course of 2021 | An IPPC call should be issued |
| - Development of key messages/facts and figures to share with industry | ALL | Over the course of 2021 |  |
| - NASCI/WB webinars with specific industry sectors to conduct outreach and to collect specific commodity/sector input | Wendy, Wendy, Shane | September-October 2021 | Wendy Beltz: The North American Sea Container Initiative has given webinars to the World Shipping Council, Global Shippers Forum, International Cargo Handling Coordination Association, and the Freight Management Association of Canada |
| - NASCI workshop NPPO and Industry | Wendy, Wendy, Shane | Sometime in 2021 |  |
| - Deliver NPPO workshop to discuss challenges, generate ideas on next steps and collect suggestions for measures | ALL | Virtually 2021 | Shane could coordinate workshop and Wendi, Rama and Wendi, Sina will come up with suggestions and consider feasibility |
| - Develop generic presentation on the risks associated with movement of sea containers and their cargos for NPPOs to share with different stakeholders | ALL | June | Might be based on the SCTF update used in 2020 for the IPPC RWs Consider how to use the video presentation developed for 2020 IPPC RWs |
| - Preparation and delivery of a presentation for the CCC-7 meeting on sea containers cleanliness and on the SCTF/Phytosanitary community work on the issue | Secretariat | 6-10 September 2021 |  |
| Output/Work Area IV – Elaboration of recommendations to CPM |  |  |  |
| Expected outcome: Recommendations to CPM how address the risks of sea containers elaborated and final report of the SCTF submitted |  |  |  |
| Action Item | Action Party | 2021 | Comments |
| - Provide inputs to the revision of the CPM recommendation 06 on Sea containers: https://assets.ippc.int/static/media/files/publication/en/2017/08/R_06_En_2017-08-23_Combined_UZOHKA3.pdf |  | May 2021 | Pending CPM 15 (2021) decision Guanghao Gu (Grace): when revising the “ Sea Containers” (R-06,2017), It is suggested that the “The IPPC Sea Container Supply Chains and Cleanliness: An IPPC Best Practice Guidance on Measures to Minimize Pest Contamination” will be added into the recommendation as annex |
| - Elaboration of options/recommendations/considerations that outline the pros and cons of each option for CPM on how address the risks of sea containers. This should include suggestions on incentive programmes to be in place at national level to promote national surveys | ALL | October 2021 |  |
| - Elaboration of final report on SCTF activities and submission of recommendations for the CPM to the IC | ALL | December 2021 |  |
| - SCTF virtual meetings | ALL | April, September, December 2021 |  |

Annex 1:

Preliminary surveillance report on risk associated with sea container pathway in Kenya

Executive Summary

International trade in plants and plant produce is clearly a means of introducing exotic pests into a country. However, excluding pests travelling in/on agricultural material, the bodies of empty and loaded sea containers have been associated with the movement of a variety of pests around the world. In 2018, KEPHIS conducted a surveillance to evaluate the pest risk associated with sea container pathway. Although the sample size was small, the surveillance finds clearly showed that the pathway presents significant biosecurity risk to Kenya. The main objective of current surveillance was to increase the sample size and further assess risks associated with the pathway including: the nature and frequency of bio contaminants, particularly plant pests; the level of biosecurity risk posed by the sea container pathway; and the effectiveness of the cargo transport units (CTU) code in preventing contamination. Using a questionnaire developed by the IPPC, a survey of 323 sea containers was undertaken at 6 entry points in Kenya between July, 2020 and February 2021. Data was recorded using the ODK software and submitted to server for analysis. Approximately 58.5% of the containers surveyed contained bio-contaminations. Soil was the main type of contaminant seen, and was found on an estimated 51% of the contaminated Containers. Approximately 37.4% of the contaminated containers were found with plant materials, 7.7% with live insects, and 4.3% with undeclared plant material cargo. Most of the live insects were found in/on empty containers, thereby representing the highest risk of the three container categories. Identification of the insect samples collected from the containers is on-going. Plants and soil samples are also being analysed for possible pests. The preliminary survey findings shows that the bio-security risks associated with sea containers are diverse. The findings also suggest that the current mitigations measures (CTU code) put in place by shipping industry to manage contamination in sea containers are not adequately addressing the challenge. Based on these findings, it is clear that the sea container pathway poses significant plant bio-security risk to Kenya. Full findings and recommendations will be made once the surveillance is completed.