CPM Focus Group on Plant Health in the context of One Health Workplan

This workplan was developed on the basis of the terms of reference of the focus group, approved by CPM-18 (2024), and to remain active until CPM-20 (2026).

*** The establishment of the focus group, ensuring full membership, took longer than anticipated. This delay is reflected in the timeline of the activities.

| Activities and sub-activities | Outputs | Lead/Responsible | Target timeline | Progress |
| --- | --- | --- | --- | --- |
| - Preliminary study on how plant health contributes to One Health approach |  |  |  |  |
| - Launch a call for national and regional case studies related to plant health in the context of One Health | National and regional case studies collected | IPPC Secretariat | Q1-2025 | Completed |
| - Hire an international phytosanitary expert with expertise in One Health to conduct the study/ in-kind support | The expert is hired/ in kind support is received | IPPC Secretariat | Q2-2025 |  |
| - Conduct desk research to understand interrelations and interdependencies between plant health and the other pillars of the One Health approach | Desk research is conducted | IPPC Secretariat/ International Phytosanitary Expert | Q2-2025 |  |
| - Coordinate with the steering group on Pest Outbreak Alert and Response Systems, the CPM Focus Group on Climate Change and Phytosanitary Issues, and other relevant focus groups and CPM, United Nations or FAO bodies to draft the study | Coordinated with all relevant groups, and inputs received | IPPC Secretariat/ CPM Focus group on Plant Health withing the context of One Health/ International Phytosanitary Expert | Q2/ Q3-2025 |  |
| - Publish the preliminary study | Report is prepared and published | IPPC Secretariat/ International Phytosanitary Expert | Q4-2025/ Q1 2026 |  |
| - Communication and advocacy |  |  | Ongoing activity from 2024 |  |
| - Develop an action plan to communicate and advocate “Plant Health” as one of the pillars of One Health | An additional component of the IPPC Communications Strategy dedicated to One Health is developed, on the basis of the content of the study | IPPC Secretariat/ CPM Focus group on Plant Health withing the context of One Health | Q4-2025 |  |
| - Develop a strategic plan for enhancing IPPC participation, advocacy, and effectiveness in the FAO One Health Committee structure and activity | Strategic plan is developed | IPPC Secretariat/ CPM Focus group on Plant Health withing the context of One Health | Q2-2025 |  |
| - Coordination, reporting and governance |  |  |  |  |
| - Advice on the organization of a CPM side session on plant health within One Health approach | Side session organized | IPPC Secretariat/ CPM Focus group on Plant Health withing the context of One Health | Q1-2025 | Completed |
| - Consider whether a formal CPM Recommendation (on AMR or general on OH) would be of use and value and, if so, provide an outline of what it may address | Recommendation on the benefit of CPM Recommendation is developed if necessary. | IPPC Secretariat/ CPM Focus group on Plant Health withing the context of One Health | Q3/ Q4-2025 |  |
| - Present to the 2025 SPG meeting the advice on the potential value and content of a CPM recommendation (on AMR or general on OH) and provide an outline of its content | Presentation of the assessment on the relevancy of CPM recommendation on AMR, and the outline of the CPM Recommendation on AMR | IPPC Secretariat/ CPM Focus group on Plant Health withing the context of One Health | October 2025 (SPG 2025) |  |
| - Present any other observations or recommendations to CPM-20 as deemed appropriate in relation to defining and recommending a CPM engagement strategy on One Health. | CPM is regularly updated | IPPC Secretariat/ CPM Focus group on Plant Health withing the context of One Health | Q1-2026 |  |

***Purple highlight indicates revision to the workplan following the CPM-19 (2025) decisions related to assessment to understand if a CPM recommendation on AMR is relevant to plant health community or not.